COMMITTEE CHARTER

For the leader forming the committee. Fill this out before the first meeting and give it to the chair and members, so everyone knows what you are asking for. Replace the gray text.

Committee

Committee name: Name of the committee.

Chair: Who leads it. Consider naming a co-chair who will take over next term.

Members: Who serves, and the skill or perspective you chose each person for.

Reports to: Who receives the committee’s work. Usually you.

Term: Start and end date, and when members rotate off.

Meets: How often and how long you expect them to meet. Example: monthly, 60 minutes.

Resources: Budget, staff support, or data you will provide.

Charge

In a short paragraph: what you are asking this committee to do and why it matters now; what it can decide on its own and what it should bring to you as a recommendation; and what you need handed back when the work is done.

Milestones and Check-Ins

The steps in the order they need to happen, with dates. Mark the ones where the committee checks in with you before moving on.

| Milestone | Date |
| --- | --- |
| Example: First meeting; charter reviewed with the committee | Sept 5 |
| Example: Check-in with me: recommendations reviewed before the committee moves ahead | Oct 1 |
| Final work handed back to me |  |

Close-Out

What success looks like: What should be different by the end of the term?

At the end of the term: Hand off, renew, or sunset. Who chairs next?

COMMITTEE CHARTER: SAMPLE

A completed example from a school director. The committee, people, and dates are fictional.

Committee

Committee name: Faculty Development Speaker Committee

Chair: Dr. Lena Ortiz. Co-chair: Dr. Sam Patel

Members: Dr. Grace Kim, Prof. David Moss, Dr. Ana Reyes

Reports to: School director

Term: Aug 2026 to May 2027. Two members rotate off each May.

Meets: Monthly, 60 minutes

Resources: $6,000 speaker budget; event support from the school office

Charge

The committee will bring in three speakers during the 2026–27 academic year to support faculty conversations on curriculum and student learning, two priorities in the school’s strategic plan. The committee selects speakers and topics. The final schedule and budget require director approval. Room scheduling and contracts are handled by the school office. A one-page summary of attendance and faculty feedback is due to the director by April 30 and will inform whether the series continues.

Milestones and Check-Ins

| Milestone | Date |
| --- | --- |
| First meeting; charter reviewed with the committee | Aug 28 |
| Faculty survey on topic interests complete | Sept 10 |
| Check-in with director: recommended list of three speakers, with topics and fees | Sept 30 |
| Speakers contacted and three events confirmed on the calendar | Nov 1 |
| Check-in with director: midpoint review | Jan 15 |
| Summary of attendance and faculty feedback due to director | Apr 30 |

Close-Out

What success looks like: At least half the faculty attend one event, and two topics carry into department meetings.

At the end of the term: Renew. Sam Patel chairs next year, and two new members join.